## Task Tracker
At Risk | Task | Description | Status
| safeScope Project | Human-Construction Machinery Proximity Detection and Personal Protective Equipment (PPE) Monitoring System | In Progress
| Project Planning and Requirements Analysis | MONTH 1 | Complete
| Literature Review For YOLO Models | Research versions of YOLO models to obtain most accurate results | Complete
| Literature Review For Training Environment | Researching model deployment environments such as Google Colab,AWS SageMaker Studio Lab,Kaggle etc. | Complete
| Literature Review For Best Tips For Training a YOLO Model such as Augmentations, Albumeniations etc | Research ultraliytics documents, github , medium blogs for best training phase | Complete
| General Literature Review | Investigate current human-machine proximity detection studies and PPE detection methods. Focus on identifying the problem, methodology, dataset, and real-time web integration discussed in research papers. | Complete
| Data Collection and Preprocessing | MONTH 2 | In Progress
| PPE Equipment Dataset Gathering | Find dataset which contains PPE equipments such as helmet,safety vest,safety suit,gloves,glasses etc. and person images | Complete
| Construction Vehicle Dataset Gathering | Find dataset which contains construction vehicles such as excavator,dump truck,cement truck,compactor,dozer,cranes etc. | Complete
| Combining both PPE and Construction Vehicle Datasets as A Single Dataset | Merge PPE and Construction vehicle datasets as a single dataset. | In Progress
| Find test videos on Youtube which contains construction vehicles,persons and PPE equipment | test videos will be founded on Youtube | In Progress
| Find test images which contains construction vehicles,persons and PPE equipment. | Test images will be founded on Roboflow or Kaggle | In Progress
| Detecting Corrupted Images and Labelling Misslabels | Since two dataset are combined as a single dataset,some labels are missing.Fix the missing labels by using labelling tools. | In Progress
| Uploading dataset to google drive, path configuration to train model on google colab | All dataset,test images and test videos will be uploaded to google drive. | Not Started
| Model Development (PPE Detection and Proximity Approximation), Inference and Testing Phase | MONTH 3 | Not Started
| Model Training | Model will be trained | Not Started
| Model Inference | Model inference will be performed | Not Started
| Model Testing | Model will be tested manually by viewing test images and videos results. | Not Started
| Model Results | Model statistics will be evaluated.If the results not satisty the developers and supervisors, model will be retrained. | Not Started
| Receive feedback from supervisor | All results of the model will be submitted to project supervisors | Not Started
| PPE Violation Algorithm,Proximity Violation Algorithm,System Integration, Database Connection,Logs, Optimization,Web Development,API Development,Customer Feedback | MONTH 4 | Not Started
| Implement PPE Violation Detection Algorithm | PPE detection algorithm will be implemented | Not Started
| Implement Proximity Violation Detection Algorithm | Proximity detection algorithm will be implemented | Not Started
| System Integration | PPE and Proximity Detection modules will be integrated into a single system. | Not Started
| API Designing | The necessary API will be designed to integrate model outputs into the website. | Not Started
| Firebase Connection and Logs | Firebase connection and keeping logs via json file format will be done | Not Started
| UI | A dashboard is designed where they can view the results of the model in real time. | Not Started
| Backend | Backend development will be done. | Not Started
| Optimization | The website and model will be optimized to work on end systems. | Not Started
| Web Development | Website to be developed for safeScope | Not Started
| Customer Feedback | User interactions on the website are tested and user feedback is received. | Not Started