## Task Tracker
At Risk | Task | Description | Status
| safeScope Project | Human-Construction Machinery Proximity Detection and Personal Protective Equipment (PPE) Monitoring System | In Progress
| Project Planning and Requirements Analysis | MONTH 1 | In Progress
| Task Allocation | Assign tasks based on team members' expertise areas | Complete
| UI Design Requirements | Determine the requirements for a web interface where users can select which PPE they want to detect. | In Progress
| Market Research | Research existing AI-powered occupational safety products in this domain. | In Progress
| Literature Review | Investigate current human-machine proximity detection studies and PPE detection methods. Focus on identifying the problem, methodology, dataset, and real-time web integration discussed in research papers. | In Progress
| Documentation | Compile all findings into a structured report to be included in the final project documentation. | Not Started
| Data Collection and Preprocessing | MONTH 2 | Not Started
| Dataset Gathering | Search for datasets containing videos and images of PPE and industrial machinery. Open-source datasets will be prioritized, and if datasets contain separate objects, they can be combined. | Not Started
| Web Design Mockup | Begin designing the website and create a simple mockup where users can select the PPE objects they want to detect. Users should be able to choose the object(s) for detection easily. | Not Started
| Model Development (PPE Detection) | MONTH 3 | Not Started
| Model Selection | Choose a deep learning-based model for PPE detection. This decision will be guided by literature research and the model deemed most effective. | Not Started
| Model Training and Evaluation | Train the selected model on the PPE dataset and initiate performance evaluation/improvement. | Not Started
| API Infrastructure | Start designing the API infrastructure required for real-time model operation. | Not Started